## Lead
ONLINE MOVIE TICKECT BOOKING
Group Number - 7
Team Lead -Sai Bhargav and Frontend Lead- Angel lenin
Backend Lead - Susmitha

## Status Track
Sl no. | Employee ID | Name | Domain | Module | 2022-10-21 | 2022-10-22 | 2022-10-23 | 2022-10-24 | 2022-10-25 | 2022-10-26 | 2022-10-27
1 | 2530061 | Angel Reginald Lenin | Front -end | Login | ER Diagram ,Database, Division of domain | Model,Repository | Service | Exception,Integration | Login Components | Final Output | Preparation
2 | 2528316 | Sushmitha P | Back-end | Controller | ER Diagram ,Database, Division of domain | Movie Bean | Repository | Controller | Theatre Bean | Final Output | Preparation
3 | 2529917 | Harshini A | Back-end | Controller | ER Diagram ,Database, Division of domain | Booking | Book Seat Controller | Repository | Controller | Final Output | Preparation
4 | 2530164 | Heera Mani K B S | Back-end | Controller | ER Diagram ,Database, Division of domain | User Bean | Controller | User Bean Controller | Repository | Final Output | Preparation
5 | 2528297 | Manushree N | Testing | user | ER Diagram ,Database, Division of domain | Model,Repository | Clientside | Server side | Database | Testing the code | Preparation
6 | 2528737 | Palepu Suresh Kumar | Front-end | Show | ER Diagram ,Database, Division of domain | Model,Repository | NMS Cinema | Active show | Seat Booking | Final Output | Preparation
7 | 2528275 | Muradsabgari Shaik Firoz | Testing | Admin | ER Diagram ,Database, Division of domain | Model,Repository | Clientside | Server side | Verification of the code | Testing the code | Preparation
8 | 2528380 | Kottagundla Sai Bhargav | Front-end | Admin | ER Diagram ,Database, Division of domain | Model,Repository | ADD Movies and Theatre | EDIT Movies and theatre | ADMIN Movies | Final Output | Preparation
9 | 2530349 | Jeevapradhap J | Front-end | Payment | ER Diagram ,Database, Division of domain | Model,Repository | Booking Confirmation | Payment | Payment Page | Final Output | Preparation

## Status Meeting
Status Meeting Group - Online Movie Ticket Booking
Meeting Date | Time | Progress Check | Time | Problem Solving | Time | Collaboration
2022-10-21 | 9:30 | a | 16:30 | a | 18:20 | a
2022-10-22 | 9:30 | a | 17:00 | a | 18:30 | a
2022-10-23 | 9:30 | a | 16:00 | a | 19:10 | a
2022-10-24 | 9:30 | a | 17:00 | a | 19:30 | a
2022-10-25 | 9:30 | a | 17:30 | a | 19:00 | a
2022-10-26 | 9:30 | a | 17:30 | a | 19:00 | a
2022-10-27 | 9:30 | a |  |  | 19:00 | a